## Slide 1: Workshop on RPTIS Data Migration RE-ENTRY ACTION PLAN
June 20 – 24, 2022

## Slide 2: Action Plan
Finalize Migration Script
Data Migration Testing
Assessor’s User Training
Pre Production Preparation
Production Migration
Rollout and Implementation

## Slide 3: Action Plan Time Line
Activity | Start | End | Person Responsible
Finalize Migration Script | June 27, 2022 | Aug 26, 2022 | Rameses, BICTO, Province and Municipal IT
Data Migration Testing | Aug 29, 2022 | Sept 2, 202 | BICTO, Province and Municipal IT
Assessor’s User Training | Sept 5, 2022 | Sept 9, 2022 | BICTO,PASSO, MASSO, IT

## Slide 4: Action Plan Time Line
Activity | Start | End | Person Responsible
Pre-Production Preparation | Sept 12, 2022 | Sept 23, 2022 | Rameses, BICTO, PASSO & MASSO
Production Migration | Sept 26, 2022 | Sept 29, 2022 | Rameses, BICTO, Province and Municipal IT
Rollout and Implementation | Sept 30, 2022 | Sept 30, 2022 | PASSO & MASSO